NARRATIVE PROGRESS REPORT

| Organization submitting the Report | UNION DE SOLIDARITE D’AIDE AU DEVELOPPEMENT COMMUNAUTAIRE (USADEC) |
| --- | --- |
| Name and title of the contact person | MAHORO RUBIBI Alexis ;Executive Director |
| Project Title | Strengthening Civic participation in the prevention and resolution of family conflict in BUGARAMA Sector |
| Reporting Period | March –July 2024 |
| Project Location | RUSIZI i District ,BUGARAMA Sector |
| Submitted to | Never Again Rwanda |
| Contact details | Phone: +250 788642109 E-mail :usadec19@gmail.com |
| Date of report submission | July 10 ,,2024 |

# EXECUTIVE SUMMARY

The project of Strengthening civic participation in the prevention and resolution of family conflict meet with 12th resolution of the 18th National Dialogue Council - Umushyikirano  and focuses on building strong and secure families . The project is implementing   in  BUGARAMA  Sector ,RUSIZI  District from March  to July  2024  by USADEC in partnership with Never Again Rwanda .

The main objective of the project is contributing in building strong and secure families with focus on preventing   and resolving family conflicts

The specific objectives are

- To strengthen  stakeholders  including  local authorities, FBO leaders and community in challenging causes of conflicts and family violence that prevail in the project area

- To enhance and contribute to conflict prevention and resolution engaging women, men, youth and other members of the community through media campaigns and dialogues.

- To contribute to the reduction and mitigation of family conflicts through mutual and peaceful conflict resolution measures and social support

The  final reporting period covers the project  activities implemented during the first  and second instalment  of the project  from  March  to July  2024   specifically

1 - introduction of the project to local authorities and stakeholders at   BUGARAMA   sector and  RUSIZI  District  level  to justify the context,  relevance and objectives of the project, the role of all and everyone in the project  implementation , monitoring and evaluation;

2- Conduct KAP baseline survey of 3 days to carry out an assessment on the existence of family conflicts and Knowledge attitude, and practice from 45 persons about conflict prevention and resolution within the project beneficiaries from 3 cells of BUGARAMA sector   to analyse the current situation on family conflicts which prevails in the project area.

KAP baseline survey has documented the current situation with a tangible number of conflict cases to be resolved.

3- Organisation of 2 stakeholders meetings

The 2 days  meeting   has involved 15 Stakeholders including Village chefs , Cell executives , youth leader   ,Executive Secretary of sector, , Community mediation and conﬂict  resolution committees ,religious leaders) selected from BUGARAMA Sector to inform them  from the  baseline survey  results  and  peace building processes to support behaviour change initiatives and advocacy for change in families, Thus a joint action has been developed and validated  aiming at enhancing family conflict prevention and resolution and  setting up strategies for its dissemination .

4- Development of a Training  manual/guide

To prepare a training of trainees   a simplified training manual with information to address and change mind set among families about domestic conflicts has been developed .

This  manual has been  used  during and after the training to guide the trainees who  serving agents of change in facilitating community dialogues with peers. This manual focus on conflict prevention and resolution and helps the trainees to facilitate conflict prevention and resolution initiatives and mobilize   community members

5- Organisation of training of 12 trainers on family conflict prevention resolution

The training of 2 days has gathered 12 trainees in BUGARAMA sector (6 women, 3 men, 3 people with disabilities). The training covered the topics on family conflict prevention, management and resolution.

6-Organize community dialogue on conflict prevention and resolution in 3 cells.

This activity is performed in terms of debates whereby 2 peace clubs encounter with themes focusing on conflict prevention and resolution in 3 cells. This activity gathers a large number of people approximately 120 per cell during UMUGANDA, UMUGOROBA W’UMURYANGO, and INTEKO Z’ABATURAGE. And it creates platform for speaking out on violence, gender equality. Women need to be trusted and be engaged in decision making processes and given some level of trust after being empowered. This is why USADEC believes that women need conflict management strategies and skills to be responsible citizens since it will reduce family stress and tensions as well as create peace environment for the society.

7-Media campaign

USADEC works in 3 villages in three cells of Bugarama sector but its ambitious goal is to reach out to many villages, cells and sectors all over the Rusizi district, which is the reason why media is the best way to get to those we can’t reach out to directly.This activity consists of disseminating the message of family conflict prevention and resolution on radio talk shows. The first alternative used is to choose 2 to 5 people to go to radio stations (Community Radio Rwanda or African FM Radio) with a journalist and address followers on different topics of family conflict prevention and resolution, then share their success stories to inspire others.

If the budget does not allow the above activity, we plan to apply another alternative of inviting a journalist on the field to record beneficiaries success stories then broadcast and rebroadcast the talk show twice a month on the radio. The main purpose of this activity is to reach out to a bigger number through family’s testimonies as we believe that over 6000 thousands of people listen to the Country FM radio and we make sure that it is rebroadcasted to get those who missed the show the first time. It contributes to attracting potential donors as well, as the performed activities are posted on USADEC website and are recorded on CDs to be given to each and every peace club and it is tangible evidence to the impact the project is making

8- Support the poor families in income generating activities.

The rabits/hens will be distributed to 30 vulnerable families who are the direct beneficiaries of this project. To ensure good growth, better productivity and the fight against diseases of rabits/hens, kits of veterinary products (medicines, vaccines) will be purchased and distributed to 30 vulnerable families. The distribution of rabits/hens will be done by the USADEC staff in collaboration with the grassroots local authorities, including the executive secretaries of the cells as well as the village committees.

DESCRIPTION OF ACHIEVED OUTCOMES

The progress achieved against planned project outcomes are described as follows

Outcome 1: The project results and lessons learnt are properly collected, analysed and documented

The KAP baseline survey report contributed to highlighting the current situation of family conflicts which prevails in BUGARAMA sector.  The key causes and consequences resulting from family conflicts are identified ,   Number of households  living in  domestic conflict are targeted  at  village and cell level (3-5 families in each village in average )   and the strategies to be taken and interventions to be carried out are agreed with stakeholders  to deal with them. This will allow to assess the relevance and efficiency of the project implementation and the management and effectiveness of the project objectives and results, as well as to identify potential prospects for sustainability and recommendations to promote the Project’s results at the end of the project

Outcome 2: Increased ownership and participation of stakeholders in the prevention and resolution of family conflicts processes

The introduction of the project to the local authorities of RUSIZI district and  BUGARAMA  sector and stakeholders allowed them to understand the relevance of the project to take ownership of the project and to commit to actively participating in the execution and monitoring and evaluation for achieving its objective

The presentation of the KAP baseline survey reports to local authorities  and  stakeholders and their information on the current situation of family conflicts which prevails in BUGARAMA Sector  ; causes and consequences of family conflicts  are identified, ,number of cases of families living in conflicts are targeted  this  allowed stakeholders  to become more involved in the prevention and resolution of conflicts family conflicts  . Thus local authorities and stakeholders   attending the 2 days meeting   have  developed and validated a joint action plan aiming at the prevention and resolution of family conflicts and they committed to implementing this action plan which will be evaluated at the end  of July 2024 .  The local authorities and stakeholders are also committed to integrating into their interventions  the prevention and resolution of family conflicts with active participation of the community  They also engaged  to strengthening the civic  participation in the prevention and resolution of family conflicts through existing mechanisms such as UMUGANDA, UMUGOROBA W'UMURYANGO, INTEKO Y'ABATURAGE at village level.

Outcome 3: The 12 trainers of peace increased their knowledge and facilitate trainings on family conflict prevention and resolution

The 12 trainers of trainees have certificates and sufficient   Knowledge and ability to solve family conflicts in an effective way.  Trained participants are become  focal points in their villages to facilitate the rest of the group that didn’t get the opportunity to attend the training and are able to  conduct community dialogues on family conflict prevention  and resolution in their respective communities/villages through UMUGANDA, UMUGOROBA W’UMURYANGO, INTEKO Z’ABATURAGE  The trainers of trainees   have   guide  manual  focused  on conflict prevention and resolution to use after the training to facilitate them  to conduct community dialogues  and undertake to facilitate conflict prevention and resolution initiatives and mobilization .

Outcome 4: Increased knowledge of the community on family conflict prevention and resolution.

As part of increasing the knowledge and skills of the community on the prevention  and resolution of  family  conflicts,  the community dialogues were organized for this purpose and brought together the population of  3  cells of BUGARAMA sector  (PERA, NYANGE and RYANKANA cells)

The community dialogue took place at the big player ground of RYANKANA cell on July 3, 2024. Thus the population, local authorities at village cells, and sector, level   religious leaders, coordinator of Never Again Rwanda in RUSIZI district as well as   families in conflict all were present

The community dialogue was facilitated by Agnes NYIRANGIRIMANA in collaboration with previously trained community facilitators

Local population has been sufficiently informed about the causes of family conflicts and the consequences that result from them. Thus, in collaboration with local authorities and stakeholders, they have committed to actively participating in the prevention and resolution of family conflicts through the delivery of the information in time and, mediate families in conflict

Outcome 5: The socio-economic conditions of vulnerable families in domestic conflicts are improved (incomes increased and healing of hearts). Vulnerable families at high risk of family conflicts and those victims of family conflicts as well as community leaders benefited from farmed rabbits and basic veterinary products to increase income.

It was noted that poverty is both a key factor in family conflict and that family conflict causes  poverty.

Rabbit breeding was chosen for the following reasons:

It constitutes an income-generating activity

the rabbit is an early breeding species which does not require large investments in terms of feeding, vaccination and treatment of animal pathologies

rabbit meat is highly appreciated by consumers and the related market is assured

Rabbit manure is very effective in improving soil productivity and increasing agricultural production

PROGRESS AGAINST PLANNED ACTIVITIES

The activities implemented in the first  milestone  (March-April 2024)  focused on KAP  Baseline Survey, 2 days  Meetings with stakeholders ,Development of Module guide for training   and effective training . Below is the detailed description of the activities implemented   in the first milestone of the project

Activity 1: Conduct KAP Baseline survey in BUGARAMA sector

In line with the project objectives, USADEC has carry out an assessment on the existence of family conflicts by  KAP  (Knowledge, attitude, and practice) about conflict prevention and resolution within the project beneficiaries from  3 cells of BUGARAMA  sector. Such as NYANGE,PERA and RYANKANA .The activity has conducted par 3 staffs of USADEC namely  MAHORO RUBIBI Alexis (Executive Director), RUBAYIZA Jean Baptiste (project field officer) and NYIRANGIRIMANA Agnes (Monitoring and Evaluation officer)

The objective of this activity is to conduct a 3 days rapid survey  from 45 persons with 24 men and 21 women   including   stakeholders  local authorities. The  information from  this baseline has been shared with local   leaders and stakeholders  for  peace building  processes . This  help to support behaviour change initiatives and advocacy for change in families.  The data collection  has been conducted  in March 22,25 and 26,2024  and focused on a Questionnaire

The target Group  sampled  includes  Executive  secretary of cells/ SEDO, Villages coordinators /security in charge at village level, IZU, CNF, CNJ ,Mediator ,and  persons from families  living in domestic conflict .

The key  findings  from baseline survey are :

- Cases of family conflict: the majority of participants indicated that at least in the village they can easily identify 3 to 5 cases of acute family conflict in  average.

- Attitudes and practices characterizing family conflict: Infidelity between spouses, poor management of domestic economic resources, disputes and fights, confrontation and aggression, between spouses and children,  alcoholism and drunkenness, consumption of drugs ,expulsion

- Causes of family conflict: drunkenness/alcoholism, infidelity between spouses, inequality in the management of domestic economic resources, lack of responsibility, lack of respect between spouses, poor interpretation and understanding of the concept Gender equality and gender equity, poverty

- Consequences of family conflict : Child delinquency, children dropping out of : school, poverty, child malnutrition, killings and  between spouses, suicide, depreciation , conception of early pregnancies among young girls and drug use among boys

- Strategies for preventing family conflict:, capacity building (training), sensitization and community mobilization, heavy sanctions for actors of domestic violence, providing information in time to denounce families  in conflict, socio-economic support for vulnerable households at high risk of family conflicts community ownership and commitment in the prevention and resolution of family conflicts

- Strategies for eliminating  family conflicts: close Community education on family conflict, preservation of laws governing the cohabitation of spouses, socio-economic support for households

- Actors in the process of family conflict prevention and resolution: family members (husbands, wives, children), local authorities of isibo, village and cell, opinion leaders, security institutions/police, RIB, organization of religious society, CSOs , entire community

Photos of participants in KAP Baseline Survey

Activity 2: Organizing meeting with stakeholders

The activity has been executed in 2 days from 27 to March ,28 ,2024 in BUGARAMA   sector  and gathering 15 stakeholders with 9 Male  and 6 .female     including   Executive Secretary (1) of sector, 3 cells Executives secretary  3 villages coordinator ,religious leader(2),CNF(1) ,youth leader (1) ,CNDP,(1)    mediation  and  conflicts    resolution committees (3)    The meeting has been facilitated by MAHORO RUBIBI Alexis Executive Director of USADEC in collaboration with RUBAYIZA Jean Baptiste Project Field Officer  .The objective of Activity was   to present  KAP baseline survey reports to   stakeholders and their information on the current situation of family conflicts which prevails in the project area , causes and consequences of family conflicts   identified, ,number of cases of families living in conflicts  targeted .Thus   stakeholders are committed to  become more involved in the prevention and resolution of conflicts family conflicts  .

The stakeholders    attending the 2 days meeting   have  developed and validated a joint action plan aiming at the prevention and resolution of family conflicts and they committed to implementing this action plan which will be evaluated at the end  of July 2024 .  The local authorities and stakeholders are also committed to integrating into their interventions  the prevention and resolution of family conflicts with active participation of the community  They also engaged  to strengthening the civic  participation in the prevention and resolution of family conflicts through existing mechanisms such as UMUGANDA, UMUGOROBA W'UMURYANGO, INTEKO Y'ABATURAGE at village level.

The photos reflecting the implementation of  the meeting with stakeholders  to present KAP survey report

Activity 3: Validation of Module guide for training

The validation of Module guide for training has   been    organized   at BUGARAMA  sector   onMarch28.2024  (one day) and gathered 15 participants composed by local authorities  , stakeholders and potentials trainees including  9 men and  6 women   and was consisted  to update the content of training module .The activity has  facilitated  by the External  consultant in collaboration with Executive Director of USADEC and Project Field Officer

Photos of participants  in the activity of module guide validation

Activity 3: Capacity Building (training workshop)

The training took place on 2- 3/2024 and brought together 12 participants including 6 women 3 men and 3 people living with disabilities due to 4 participants from each cell of BUGARAMA Sector. The training focused on  conflict prevention and resolution and  was facilitated by an external consultant Fred Musiime

The applied  methodology focused on the  training techniques  of adults persons  such as active brain storming, round table, question- answer,  group work and plenary presentation, and  homework The  training materials were  note books, pens, scotch , markers and , projector

Training schedule

Day 1: arrival and registration of participants, opening of the training by Executive Director of USADEC and Executive Secretary of BUGARAMA Sector,, agree on the training program , setting up  the instructions and working rules, comparison of the expectations of the participants at content of the training.

The first day the training   covered the following  content

-Definition of conflict, prevention and Resolution

-Domestic violence

-Types of conflicts

-causes and consequences of family conflicts

-behaviour and practices toward family conflict

-Group work and presentation

The first training session started at 9am and ended at 3 p.m.

The 2nd day of training focused on the evaluation of the previous day.  The  content  of the training  were was  Family conflict tree,  Key tools to analyse family conflict, strategies for prevention and resolution of family conflict, ,Quality and competences  of  facilitator involved in conflict resolution ,  Development of a conjoint Action plan to be implemented by trainees as community animators after the training .  At the end of the session of  the training, the participants have an evaluation test followed by the final evaluation and distribution of certificates to participants  In his closing speech to the training, Executive Director of USADEC in collaboration with the social affairs officer of BUGARAMA sectors all urged the participants to put into practice the concepts acquired and to proceed with community mobilization on a larger scale on prevention and resolution of family conflicts through UMUGANDA, INTEKO Y'ABATURAGE AND UMUGOROBA W'UMURYANGO .

Photos of   participants receiving certificates at the end of  the training

Youth Representatives of CNJ at cell level committed to prevent family conflict

Activity 4: Organize community dialogue on conflict prevention and resolution in 3 cells.

As part of increasing the knowledge and skills of the community on the prevention  and resolution of  family  conflicts,  the community dialogues were organized for this purpose and brought together the population of  3  cells of BUGARAMA sector  (PERA, NYANGE and RYANKANA cells)

The community dialogue took place at the  big  player ground of  RYANKANA cell on July 3, 2024. Thus the population, local authorities at  village  cells, and  sector, level   religious leaders  journalists  , coordinator of Never Again Rwanda in  RUSIZI district as well as   families in  conflict all were present

The community dialogue was facilitated by Agnes NYIRANGIRIMANA in collaboration with previously trained community facilitators

Local  population  has been sufficiently informed about the causes of family  conflicts and the consequences that result from them. Thus, in collaboration with local authorities and stakeholders, they have committed to actively participating in the prevention and resolution of family conflicts through the delivery of the information in time and , mediate families in conflict

Activity 5: Support the poor families in income generating activities.

The  90 rabbits have   been  distributed to 30 vulnerable families who are the direct beneficiaries  The distribution of rabbit and veterinary product  has been  done by the USADEC staff in collaboration with the  local authorities, including the executive secretaries of the cells as well as the village committees.

GENDER MAINSTREAMING

Gender Mainstreaming into interventions is USADEC's mission-based approach. In the implementation of the activities of the first milestone of the project  women and men participated equally without any discrimination with respect for human rights and dignity:  in KAP baseline survey 24 men and 21 women were questioned and the results were satisfactory, in the restitution meeting of the results from  the KAP baseline survey among 15 Stakeholders  9 men and 6 women took part in the meeting  while in the training 6 women, 3 men and 3 people l with disabilities were trained on  family conflict prevention. Especially women and girls were strongly encouraged to participate actively in all Project activities this is because gender relations are power relations and some women and men may resist the change.  Particular attention was be paid to issues of equality, equity and gender during all phases of the project activities  Since most often women and children are victims of family conflicts, gender mainstreaming  played a key role in achieving the results. During the survey, women provided in-depth information on the key causes and consequences linked to family conflicts and the 2 days meeting of the presentation of the results from KAP survey Women contributed to the formulation   of strategies allowing the prevention and resolution of family conflicts. As women are part of the community animators as agents of peace and trainers on the elimination of family conflicts it is expected that the related results will be more tangible at the end of the project.

Likewise, out of 390 participants in community dialogues, including 140 women, 200 men, 40 youth and 10 local authorities were present

SOCIAL INCLUSION

This action was  based on the promotion of the socio-economic and cultural right provided for in the Rwandan constitution and in various laws erected particularly for the protection of the rights of  vulnerable peoples persons with disabilities, historically marginalized, children ,youth and women  and the fight against all forms of violence committed against them. In the project implementation, everything has been done to safeguard the fundamental rights of vulnerable group. The strategies adopted for changing the mentality and attitudes of the target groups employ participatory and interactive methods.

In the KAP baseline survey 21 women  against 24 men were interviewed including ,  representative of National council of youth and women at local level, representative of people with disability  community (women, men ,people with disability) are interviewed .In the meeting with stakeholders  to present the  results from survey  CNF, CNJ,NCPW  as well as the representative of the national children's council at  sector level participated in the meeting .During  the training of 12 persons  6 women and 3 people with disability participated  in the workshop because women, children, people with disabilities are the groups most confronted with the problems of family conflicts and their consequences, which is why they are integrated into project activities to participate in the formulation of solutions and strategies aiming at eliminate family  conflict and to  achieve inclusive results.

LESSONS LEARNT AND OPPORTUNITIES

Through The results of KAP Baseline survey is clear that in BUGARAMA Sector prevails a big number of cases of  family conflict :3-5  cases of acute family conflict in average  per each village .The key  Causes of family conflict identified are based  on  drunkenness/alcoholism, infidelity between spouses, inequality in the management of domestic economic resources, lack of responsibility, lack of respect between spouses, poor interpretation and understanding of the concept Gender equality and gender equity,  acute poverty

The Consequences of family conflict focus on Child delinquency, children dropping out of: school, poverty, child malnutrition, killings and between spouses, suicide, depreciation, conception of early pregnancies among young girls and drug use among boys

The stakeholders are committed to become more involved in the prevention and resolution of  family conflicts .They   have  developed and validated a joint action plan aiming at the prevention and resolution of family conflicts and they committed to implementing this action plan which will be evaluated at the end  of July 2024 .They  are also committed to integrating into their interventions  the prevention and resolution of family conflicts with active participation of the community .  Local authorities also engaged to strengthen the civic participation in the prevention and resolution of family conflicts through existing mechanisms such as UMUGANDA, UMUGOROBA W'UMURYANGO, INTEKO Y'ABATURAGE at village level

The trained community animators have agreed to be agents and catalysts of prevention and resolution of family conflicts prevention and resolution in their respective communities /Village, ISIBO through training of their peers and Mobilization in collaboration with local authorities and other stakeholders

Religious leaders constitute key actors in the prevention and resolution of family conflicts once they integrate this task into their interventions

The prevention and resolution of family conflicts concerns all actors at  local level conflict prevention and resolution: family members (husbands, wives, children), local authorities of isibo, village and cell, opinion leaders, security institutions/police, RIB, organization of religious society, entire community and entire   community which requires continuous and regular coordination

The  Strategies for preventing and resolving  family conflict focus on  capacity building (training), sensitization and community mobilization ,fighting  against domestic  violence , providing information in time to denounce families in conflict, close Community education on family conflict, preservation of laws governing the cohabitation of spouses, socio-economic support for households socio-economic support for vulnerable households at high risk of family conflicts

## CHALLENGES AND MITIGATION MEASURES

The activities of the first milestone of the project were well executed and the local authorities and population actively participated in the implementation

Below some challenges encountered The budget allocated to the implementation of activities has been de -owned compared to the current prices of services on the market, namely car rental/ (the fuel  price is expensive , the  lunch ,of participants in the training and meeting , rental  of conference hall for training and meeting  cost  for Media and mission  fees for the project staff

# To the mitigate to this challenges we have proceeded to rent less comfortable conference hall  and rental of transport vehicles at  local level

# CONCLUSION AND OUTLOOK

In view of the survey results from KAP Baseline survey conducted in BUGARAMA Sector  to the prevention and resolution of family conflicts in  BUGARAMA, USADEC recommends all partners and  institutions  working for socio-economic development in  BUGARAMA sector the following elements :

- They  would integrate into their interventions the prevention and peaceful resolution of family conflicts because family conflict constitutes an key  factor of poverty and poverty leads to violence and  family conflict

- They  would implement a joint action plan developed and validated aiming at  prevention and resolution of family conflicts as well as its regular monitoring and evaluation  to achieve the most tangible results

- Local authorities are strongly recommended to initiate the community to take ownership of the  family conflict prevention and resolution process

- The  mechanisms already in place granting space to the  community  such as UMUGANDA, INTEKO Z’ABATURAGE  and UMUGOROBA W’UMURYANGO  should be  more exploited for the prevention and resolution of family conflicts

- The IZU  (INSHUTI Z’UMURYANGO) deserve the  specific  capacity building  to be more operational and efficient

- Vulnerable families  should benefit from socio-economic support to avoid the potential  risk of family conflict

- Victims  households  of   family conflict deserve specific support for their rehabilitation and healing of hearts

- Recruitment and training  of animators for healing hearts are very needed

- Spouses who cohabit illegally should be educated to enter into legal marriage

- The causes and consequences of family conflicts in  BUGARAMA Sector,  are highlighted and the families in conflict have already been identified and located, Thus, the role of everyone proves necessary to proceed with the elimination  of family conflicts

Done at Kigali on  July  10, 2024

MAHORO RUBIBI Alexis

Executive Director  of USADEC